## Action Item Blocker Log
Action Item Blocker Log
Action Item | Owner | Risk Level | Blocker | Due Date | Status
Finalize project requirements | Alex M. | High | Waiting for client approval | 2026-04-05 | Blocked
Prepare budget report | Jamie L. | Medium |  | 2026-04-02 | In Progress
Set up QA testing environment | Chris P. | High | Test servers not provisioned | 2026-03-29 | Blocked
Update stakeholder presentation | Morgan K. | Low | Pending final metrics | 2026-04-01 | On Hold
Deploy staging build | Taylor R. | High | Build failing in CI pipeline | 2026-03-30 | Blocked
Confirm vendor contract | Jordan S. | Medium |  | 2026-04-03 | In Progress
Review compliance checklist | Casey D. | Low |  | 2026-04-04 | Open
Resolve access permission issue | Casey D. | Low |  | 2026-03-26 | Completed